## Utkarsh
Time for Completing Task
| Task | Alloted On | Estimated | Actual | Comments
1 | UI Design | 19/10/19 Saturday | 5 hours | 4.5 hours
| Home Page |  | 2 hours | 2 hours
| Login |  | 0.5 hours | 0.5 hours
| Register |  | 0.5 hours | 0.5 hours
| Userpage |  | 1.5 hours | 1 hour
| Admin Page |  | 0.5 hours | 0.5 hour
2 | User Functionalities | 19/10/19 Saturday | 6 hours | 8 hours
| Adding Amount |  | 1.5 hours | 1.5 hours
| Transfering Amount |  | 1.5 hours | 1.5 hours
| Getting Transactions |  | 1.5 hours
| Download Excel |  | 1.5 hours
3 | Diagrams | 19/10/19 Saturday | 3 hours | 2.5 hours
| E-R Diagram |  | 1 hour | 1 hour
| Sequence Diagram |  | 1 hour | 0.5 hour
| Activity Diagram |  | 1 hour | 1 hour

## Venkatesh
Time for Completing Task
| Task | Alloted On | Estimated | Actual | Comments
1 | Wireframe Design | 19/10/19 Saturday | 1.5 hours | 1.5 hours
| Home Page |  | 0.3 hours | 0.4 hours
| Login |  | 0.3 hours | 0.3 hours
| Userpage |  | 0.3 hours | 0.4 hours
| Admin Page |  | 0.3 hours | 0.3 hours
2 | Register |  | 1 hour | 3 hours
validation
| a)Validation of username |  | 0.25 hour | 0.6 hour
| b) Validation of password |  | 10 min | 10 min
| c)Validation of Confirm password |  | 10 min | 10 min
| d)Validation of Phone No. |  | 10 min | 10 min
2 | Admin Functionalities | 19/10/19 Saturday | 2 hours | 2.5 hours
| Registration |  | 1 hour | 1 hour
| Accounts to be approved |  | 0.5 hour | 0.5 hour
| Approve Account |  | 0.5 hour | 1 hours
3 | JWT | 19/10/19 Saturday | 4 hours | 6 hours
| Getting Tokens from the database |  | 2 hours | 3 hours
| Passing tokens in the headers |  | 2 hours | 3 hours